## Sheet1
Hardware
optic | qty | cost | quote | Vendor | description
SG Optics
Slits | 10 | 15000
Filters | 10 | 50000
FoldingFlat 2 | 2 | 600
FoldingFlat 1 | 1 | 500
Grating | 1 | 39100 | yes | Newport Corp | echelle, 79 g/mm, 63 deg blaze, 100x408mm
Parabola (Col) | 1 | 43600 | yes | Optical Mechanics Inc. | 0.5 m, 2200 fl, zerodur substrate, Ag coating
Scanner folds | 2 | 600
camera fold | 1 | 300
Transfer Optics
parabola | 1 | 2000
folding flat | 1 | 300
OAP | 1 | 5000
CT Optics
folding flats | 2 | 600
parabola | 1 | 1500
OAP | 1 | 3000
rotator mirrors | 3 | 1200
T/T mirror | 1 | 300
Total Optics |  | 163600
Assy (less optics) | [5 empty] | manpower (man-weeks) | mech eng | opt eng | acquisition | fabrication | elec eng | soft eng | asm/test | total labor | component cost | total cost
Dewar/Camera | 1 | 700000 |  | IR Labs | External contract, BBSO work is design and post delivery |  | 12 | 8 | 4 | 4 | 2 | 2 | 16 | 48
Slit Wheel | 1 | [5 empty] | 3 | 1 | 1 |  |  |  | 2 | 7
D Fold1 | 1 | [5 empty] | 1 |  | 1 |  |  |  | 1 | 3
D Fold2 | 2 | [5 empty] | 1 | 1 | 1 |  |  |  | 1 | 4
Grating | 1 | [5 empty] | 2 | 2 | 1 |  |  |  | 4 | 9
D Fold3 | 1 | [5 empty] | 1 | 2 | 1 |  |  |  | 1 | 5
Camera Fold | 1 | [12 empty] | 0
0
CT System | [13 empty] | 0
Image Rotator | 1 | 3000 |  |  |  |  | 4 | 2 | 2 | 3 | 2 | 3 | 4 | 20
Slit Scanner | 1 | 2000 |  |  |  |  | 4 | 2 | 2 | 3 | 2 | 4 | 4 | 21
D opt bench | 1 | 6000 |  |  | External contract, same |  | 4 | 2 | 2 |  |  |  | 4 | 12
Camera OAP | 1 | 1000 |  |  |  |  | 2 | 2 | 1 | 1 |  |  | 1 | 7
CT Beam Splitter | 1 | 600 |  |  |  |  | 2 |  | 1 | 1 |  |  | 1 | 5
CT Camera Focus | 1 | 2000 |  |  |  |  | 4 | 2 | 2 | 3 | 2 | 4 | 4 | 21
Tip Tilt Stage | 1 | 45000 |  |  |  |  | 3 | 2 | 2 | 2 | 2 | 2 | 4 | 17
Dalsa Camera | 1 | 30000 | [8 empty] | 2 | 4 | 6 | 12
0
0
Beam Transfer | [13 empty] | 0
OAP transfer mirror | 1 | 4000 |  |  |  |  | 2 | 2 | 1 | 1 |  |  | 1 | 7
parabola transfer | 1 | 3000 |  |  |  |  | 2 | 2 | 1 | 1 |  |  | 2
transfer fold | 1 | 300 |  |  |  |  | 2 |  | 1 | 1 |  |  | 2
mounting structure | 1 | 12000 |  |  | External contract, same |  | 4 | 2 | 1 | 4 |  |  | 4 | 15
Total Hardware |  | 808900 |  |  |  |  | 53 | 32 | 25 | 24 | 12 | 19 | 62 | 227
TOTALS |  | 972500
Year 1 |  | 712000
Year 2 |  | 185500
Year 3 |  | 75000
Year 4
4 Year Total |  | 972500

## Sheet2
Manpower Requirements (man-weeks)
Year 1 | Task | mech eng | opt eng | acquisition | fabrication | elec eng | soft eng | asm/test | total labor
| specify dewar, camera | 10 | 6 | 2 |  |  | 2 |  | 20
| design, build mount struct | 4 | 2 | 1 | 4 |  |  | 4 | 15
| specify dewar components | 4 | 4 | 4 |  |  |  |  | 12
| totals | 18 | 12 | 7 | 4 | 0 | 2 | 4 | 47
Year 2
| Image Rotator | 4 | 2 | 2 | 3 | 2 | 3 | 4 | 20
| Slit Scanner | 4 | 2 | 2 | 3 | 2 | 4 | 4 | 21
| D opt bench | 4 | 2 | 2 |  |  |  | 4 | 12
| Camera OAP | 2 | 2 | 1 | 1 |  |  | 1 | 7
| CT Beam Splitter | 2 |  | 1 | 1 |  |  | 1 | 5
| totals | 16 | 8 | 8 | 8 | 4 | 7 | 14 | 65
Year 3
| CT Camera Focus | 4 | 2 | 2 | 3 | 2 | 4 | 4 | 21
| Tip Tilt Stage | 3 | 2 | 2 | 2 | 2 | 2 | 4 | 17
| Dalsa Camera |  |  |  |  | 2 | 4 | 6 | 12
| Integrate Dewar | 2 | 2 | 2 | 2 |  | 2 | 6 | 16
| totals | 9 | 6 | 6 | 7 | 6 | 12 | 20 | 66
Year 4 | Integrate Dewar |  |  |  | 8 | 5 | 6 | 15 | 34
| Install Dewar |  |  |  | 8 | 5 | 6 | 5 | 24
| totals | 0 | 0 |  | 16 | 10 | 12 | 20 | 58